## Sheet1
February |  |  |  | March
W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12
DADIU PRODUCTION!
Skeletal structure | Redisign of the skeletal structure and editor | Continue on the structure |  |  | RayTracing optimization | RayTracing optimization | RayTracing optimization
Surface representation
Visualisation by tesselation |  | Brute force ray tracing of the structure | Design of Ray tracing algo
Draft of skeletal data structure | More primitives and convolution |  |  | Design of Ray tracing algo
Raytracing of skeletal structure with balls and tubes
Raytracing of a single metaball
Raytracing of a single metatube
April |  |  |  | May
W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20
Improve shader
RayTracing optimization | RayTracing optimization | Texturing |  | Texturing | Texturing | Animation of the tree structure | Fix
|  | Design texturing method | Design texturing method |  |  | Might broke raytracing and texturing
June |  |  |  | July
W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28
Fix | Integrate in classical pipeline | Shader effects | Shader effects | Shader effects | Shader effects | Writting | Writting
[6 empty] | Polishing | Polishing
August
W29 | W30
Writting | Writting
Polishing | Polishing

## Sheet2
Work Chunks
Editor Prototype
Primitives
Sphere
Cylinder